REQUEST FOR PROPOSAL

for

Engagement of Consulting Agency for

Development of Satellite Sanskrit TV Channel for Uttarakhand Sanskrit Academy, Department of Sanskrit Education, Haridwar

On

Public Private Partnership (PPP) Mode

Due Date: 7th January, 2020

Uttarakhand Sanskrit Academy,

Department of Sanskrit Education,

Haridwar

# DISCLAIMER

The information contained in this Request for Proposal document (“RFP”) or subsequently provided to Applicants, whether verbally or in documentary or any other form by or on behalf of the Authority or any of their employees or advisers, is provided to Applicants on the terms and conditions set out in this RFP and such other terms and conditions subject to which such information is provided.

This RFP is not an agreement and is neither an offer nor invitation by the Authority to the prospective Applicants or any other person. The purpose of this RFP is to provide interested parties with information that may be useful to them in the formulation of their Proposals pursuant to this RFP. This RFP includes statements, which reflect various assumptions and assessments arrived at by the Authority in relation to the Consultancy. Such assumptions, assessments and statements do not purport to contain all the information that each Applicant may require. This RFP may not be appropriate for all persons, and it is not possible for the Authority, its employees or advisers to consider the objectives, technical expertise and particular needs of each party who reads or uses this RFP. The assumptions, assessments, statements and information contained in this RFP, may not be complete, accurate, adequate or correct. Each Applicant should, therefore, conduct its own investigations and analysis and should check the accuracy, adequacy, correctness, reliability and completeness of the assumptions, assessments and information contained in this RFP and obtain independent advice from appropriate sources.

Information provided in this RFP to the Applicants is on a wide range of matters, some of which depends upon interpretation of law. The information given is not an exhaustive account of statutory requirements and should not be regarded as a complete or authoritative statement of law. The Authority accepts no responsibility for the accuracy or otherwise for any interpretation or opinion on the law expressed herein.

The Authority, its employees and advisers make no representation or warranty and shall have no liability to any person including any Applicant under any law, statute, rules or regulations or tort, principles of restitution or unjust enrichment or otherwise for any loss, damages, cost or expense which may arise from or be incurred or suffered on account of anything contained in this RFP or otherwise, including the accuracy, adequacy, correctness, reliability or completeness of the RFP and any assessment, assumption, statement or information contained therein or deemed to form part of this RFP or arising in anyway in this Selection Process.

The Authority also accepts no liability of any nature whether resulting from negligence or otherwise however caused arising from reliance of any Applicant upon the statements contained in this RFP.

The Authority may in its absolute discretion, but without being under any obligation to do so, update, amend or supplement the information, assessment or assumption contained in this RFP.

The issue of this RFP does not imply that the Authority is bound to select an Applicant or to appoint the Selected Applicant, as the case may be, for the Consultancy and the Authority reserves the right to reject all or any of the Proposals without assigning any reasons whatsoever.

# INTRODUCTION

  - THE PROJECT

Uttarakhand Sanskrit Academy, Haridwar proposes Development of Satellite Sanskrit TV Channel for broadcasting Sanskrit content on Cable, DTH, etc  for promotion of Sanskrit language, on PPP basis. As a part of planning process Uttarakhand Sanskrit Academy, Haridwar intends to hire a Consultancy Agency for preparation of Detailed Project Report, Procurement Management & Project Management for Development of Satellite Sanskrit TV Channel in Uttarakhand (the “Project”).

The services are initially intended to be hired for a period of two years. This period may be curtailed or extended as per the requirement of Uttarakhand Sanskrit Academy, Haridwar.

  - RFP

    - Uttarakhand Sanskrit Academy, Haridwar (the “Authority”) invites Request for Proposal (RFP) (the “Proposals”) for selection of the Consultant (the “Consultant”) for Development of Satellite Sanskrit TV Channel in Uttarakhand (the “Project” ) on the Terms and Conditions mentioned in the RFP document.

    - The Authority invites Proposals from the Consultancy Agency herein collectively referred to as (the “Applicants”) who fulfill the pre qualification criteria indicated in clause 2.2 for Development of Satellite Sanskrit TV Channel in Uttarakhand (the “Project” ).

The Authority intends to select the Applicant through an open competitive bidding process in accordance with the procedure set out herein.

  - Due diligence by Applicants

Applicants are encouraged to inform themselves fully about the assignment and the local conditions before submitting the Proposal by paying a visit to the Authority and the Project site, sending written queries to the Authority, and attending a Pre-Proposal Conference on the date and time specified in Clause 1.10.

  - Procurement of RFP Document

RFP document can be obtained from the date of issue of notice till Proposal Due Date (PDD) between 1000 hrs and 1700 hrs on all working days from the address indicated at para 1.11.1. The document can also be downloaded from the official website of the Authority or www.upppc.org.

  - Validity of the Proposal

The Proposal shall be valid for a period of not less than 180 days from the Proposal Due Date (the “PDD”).

  - Brief description of the Selection Process

The Authority has adopted a single stage selection process (the “Selection Process”) in evaluating the Proposals. The Authority shall invite financial offers from the Applicants. The Financial Proposals of those applicants shall be open who fulfils pre qualification criteria indicated in clause 2.2. A financial evaluation will be carried out as specified in Clause 3.1. Proposals will finally be ranked according to their financial scores as specified in Clause 3.3 & 3.4. The first ranked Applicant (the “Selected Applicant”) may, if necessary, be invited for clarifications and reconfirmation of commitments and its obligations under this RFP, while the second ranked Applicant will be kept in reserve.

  - Currency conversion rate and payment

All payments to the Applicant shall be made in INR in accordance with the provisions of this RFP. The Applicant may convert Rupees into any foreign currency as per Applicable Laws and the exchange risk, if any, shall be borne by the Applicant.

  - Schedule of Selection Process

The Authority would endeavor to adhere to the following schedule:

| Sr. No. | Event Description | Estimated Date |
| --- | --- | --- |
|  | Last date for receiving queries/clarifications | 22nd November 2019 |
|  | Pre-Proposal Conference | 27th November 2019, 1500 hours |
|  | Authority response to queries | Secretary, Uttarakhand Sanskrit Academy, Department of Sanskrit Education,Haridwar |
|  | Proposal Due Date (PDD) (i.e last date of receiving RFP) | 7th January 2020, 1400 hours |
|  | Opening of Proposals | 9th January, 2020 |
|  | Letter of Award (LOA) | To be informed later |
|  | Signing of Agreement | To be informed later |
|  | Validity of Applications | 180 days from the Proposal Due Date |

  - Pre-Proposal visit to the Site and inspection of data

Prospective applicants may visit the Site and review the available data at any time prior to PDD.

  - Pre-Proposal Conference and Submission of Proposals

The date, time and venue of Pre-Proposal Conference shall be:

Date		: 	27 th November, 2019

Time		: 	1500 hours

Venue	: 	Uttarakhand Sanskrit Academy, Department of Sanskrit                                    Education, Sanskrit Bhawan,  NH 58, Ranipur Jhal, Jwalapur,                               Haridwar, Uttarakhand-249404

  - Communications

    - All communications including the submission of Proposal should be addressed to:

Uttarakhand Sanskrit Academy,

Department of Sanskrit Education,

Sanskrit Bhawan,  NH 58,

Ranipur Jhal, Jwalapur,

Haridwar, Uttarakhand-249404

    - Email :

All notifications would be uploaded on www.uksa.ac.in

    - All communications, including the envelopes, should contain the following information, to be marked at the top in bold letters:

“RFP for Engagement of Consultant for Development of Satellite Sanskrit TV Channel”

# INSTRUCTIONS TO APPLICANTS

- GENERAL

  - Scope of Proposal

    - Detailed description of the objectives, scope of services, deliverables and other requirements relating to this Consultancy are specified in this   RFP and Terms of Reference (TOR) attached as Appendix 1. The manner in which the Proposal is required to be submitted, evaluated and accepted is explained in this RFP.

    - Applicants shall be deemed to have understood and agreed that no explanation or justification for any aspect of the Selection Process will be given and that the Authority’s decisions are without any right of appeal whatsoever.

    - The Applicant shall submit its Proposal in the form and manner specified in this Part-2 of the RFP. The Financial Proposal shall be submitted in the format provided at Appendix 5. Upon selection, the Applicant shall be required to enter into an agreement with the Authority.

    - The Applicant should submit a Power of Attorney as per the format provide in Appendix 4.

    - Any entity which has been barred by the Central / State Government in India, or any entity controlled by them, from participating in any project, and the bar subsists as on the date of Proposal, would not be eligible to submit the Proposal.

  - Pre Qualification Criteria/Minimum Conditions of Eligibility

    - Applicants must read carefully the minimum conditions of eligibility   (the” Conditions of Eligibility”) provided herein. Proposals of only those Applicants who satisfy    the Conditions of Eligibility will be considered for evaluation.

    - To be eligible for evaluation of its Proposal, the Applicant shall   fulfill the following Minimum Eligibility Criteria:

- Technical Capacity:

- The Applicant should be in the business of providing technical & project management consultancy services for Development and Marketing of TV channels for at least five years.

- The Applicant should have successfully done similar work for at least two TV channels in past three years, out of which, with minimum total project cost of Rs. 10 Crore

- Financial Capacity:

The Applicant shall have:

- Average annual turnover of at least Rs 10 Crore or the last three financial years i.e. FY 2016-17, 2017-18 to 2018-19.

- Should have net worth (share capital plus free reserves) of at least Rs. 5 Crore as per last audited annual accounts.

Note:-

- The Application must be accompanied by the audited annual financial statements of the Applicant for the last three (3) financial years.

- The experience of any previous project should not be claimed by more than one applicant.

    - Any entity which has been barred by the Central / State Government in India, or any entity controlled by them, from participating in any project, and the bar subsists as on the date of Proposal, would not be eligible to submit the Proposal.

    - An Applicant should have, during the last three years, neither failed to perform on any agreement, as evidenced by imposition of a penalty by an arbitral or judicial authority or a judicial pronouncement or arbitration award against the Applicant, nor been expelled from any project or agreement nor have had any agreement terminated for breach by such Applicant.

    - While submitting a Proposal, the Applicant should attach clearly marked and referenced continuation sheets in the event that the space provided in the specified forms in the Appendices is insufficient. Alternatively, Applicants may format the specified forms making due provision for incorporation of the requested information.

  - Conflict of Interest

    - The selected Applicant shall not receive any remuneration in connection with the assignment except as provided in the Agreement. The Applicant and its affiliates shall not engage in consulting activities that conflict with the interest of the Uttarakhand Sanskrit Academy, Haridwar under the contract and shall be excluded from downstream supply of goods or construction of works or purchase of any asset or provision of any other service related to the assignment other than a continuation of the Services” under the ongoing contract. It should be the requirement of the consultancy contract that the Applicant should provide professional, objective and impartial advice and at all times hold the Uttarakhand Sanskrit Academy, Haridwar interest’s paramount, without any consideration for future work, and that in providing advice they avoid conflicts with other assignments and their own corporate interests. Applicant shall not be hired for any assignment that would be in conflict with their prior or current obligations to other Uttarakhand Sanskrit Academy, Haridwar, or that may place them in a position of being unable to carry out the assignment in the best interest of the Employer. Without limitation on the generality of the foregoing, Applicant  shall not be hired, under the circumstances set forth below:-

- Conflict between Consulting activities and procurement of goods, works or services: A Consultant/ Consultancy concern that has been engaged to provide goods, works, or services for a project, and each of its affiliates, shall be disqualified from providing consulting services related to those goods, works or services. Conversely, a Consultant/Consultancy concern hired to provide consulting services for the preparation or implementation of a project, and each of its affiliates, shall be disqualified from subsequently providing goods, works or services for such preparation or implementation.

- Conflict among consulting assignments: Neither Applicant (including their personnel and) nor any of their affiliates shall be hired for any assignment that, by its nature, may be in conflict with another assignment of the Applicant. As an example, Applicant hired to prepare engineering design for an infrastructure project shall not be engaged to prepare an independent environmental assessment for the same project, and Applicant assisting Uttarakhand Sanskrit Academy, Haridwar in the privatization on public assets shall neither purchase nor advice purchasers of, such assets. Similarly, Applicant hired to prepare Terms of Reference (TOR) for an assignment shall not be hired for the assignment in question.

- Relationship with Employer's staff: Applicant (including their personnel and sub- Applicant) that have a business or family relationship with such member(s) of the Employer's staff or with the staff of the project implementing agency, who are directly or indirectly involved in any part of ; (i) the preparation of the TOR of the contract, (ii) the selection process for such contract, or (iii) supervision of such contract; may not be awarded a contract unless it is established to the complete satisfaction of the  employing authority, for the reason to be recorded in writing, that such relationship would not affect the aspects of fairness and transparency in the selection process and monitoring of Applicant’s work.

  - Number of Proposals

An Applicant is eligible to submit only one Application for the Project.

  - Cost of Proposal

The Applicants shall be responsible for all of the costs associated with the preparation of their Proposals and their participation in the Selection Process. The Authority will not be responsible or in any way liable for such costs, regardless of the conduct or outcome of the Selection Process.

  - Site visit and verification of information

Applicants are encouraged to submit their respective Proposals after visiting the Project site and ascertaining for themselves the site conditions, location, surroundings, climate, access to the site, availability of drawings and other data with the Authority, applicable laws and regulations or any other matter considered relevant by them.

  - Acknowledgement by Applicant

    - It shall be deemed that by submitting the Proposal, the Applicant has:

- made a complete and careful examination of the RFP;

- received all relevant information requested from the Authority;

- acknowledged and accepted the risk of inadequacy, error or mistake in the information provided in the RFP or furnished by or on behalf of the Authority or 	relating to any of the matters referred to in Clause 2.5 above;

- satisfied itself about all matters, things and information, including matters referred to in Clause 2.6 herein above, necessary and required for  submitting an informed Application and performance of all of its obligations there under;

- acknowledged that it does not have a Conflict of Interest; and

- Agreed to be bound by the undertaking provided by it under and in terms hereof.

    - The Authority shall not be liable for any omission, mistake or error on the part of the Applicant in respect of any of the above or on account of any matter or thing arising out of or concerning or relating to RFP or the Selection Process, including any error or mistake therein or in any information or data given by the Authority.

  - Right to reject any or all Proposals

    - Notwithstanding anything contained in this RFP, the Authority reserves the right to accept or reject any Proposal and to annul the Selection Process and reject all Proposals, at any time without any liability or any obligation for   such acceptance rejection or annulment, and without assigning any reasons thereof.

    - The Authority reserves the right to reject any Proposal if:

- at any time, a material misrepresentation is made or uncovered, or

- the Applicant does not provide, within the  time specified by the Authority,  the supplemental  information  sought  by  the  Authority  for  evaluation  of  the Proposal.

Such misrepresentation/ improper response may lead to the disqualification of the Applicant. If such disqualification /rejection occur after the Proposals have been opened and the highest ranking Applicant gets disqualified / rejected, then the Authority reserves the right to consider the next best applicant, or any other measure as may be deemed fit in the sole discretion of the Authority, including annulment of the Selection Process.

- DOCUMENTS

  - Contents of the RFP

    - This RFP comprises the Disclaimer setforth hereinabove, the contents as listed below and will additionally include any Addendum / Amendment issued in accordance with Clause 2.10:

RFP

1 Introduction

2 Instructions to Applicants

3 Criteria for Evaluation

4 Fraud and corrupt practices

5 Pre-Proposal Conferences

6 Miscellaneous

7 Payment Schedule

Appendix 1: Terms of Reference

Appendix 2 : Letter of Proposal

Appendix 3 : Statement of Legal Capacity

Appendix 4 : Format For Power Of Attorney For Signing The Proposal

Appendix 5 : Financial Proposal

  - Clarifications

    - Applicants requiring any clarification on the RFP may send their queries to the Authority in writing before the date mentioned in the Schedule of Selection Process at Clause 1.8. The envelopes shall clearly bear the following identification:

"Queries/Request for Additional Information concerning RFP, Development of Satellite Sanskrit TV Channel

The Authority shall endeavor to respond to the queries within the period specified therein but not later than 7 days prior to the Proposal Due Date. The responses will be sent by fax or e-mail. The Authority will post the reply to all such queries on the Official Website and copies thereof will also be circulated to all Applicants without identifying the source of queries.

    - The Authority reserves the right not to respond to any questions or provide any clarifications, in its sole discretion, and nothing in this Clause shall be taken or read as compelling or requiring the Authority to respond to any question or to provide any clarification.

  - Amendment of RFP

    - At any time prior to the deadline for submission of Proposal, the Authority may, for any reason, whether at its own initiative or in response to clarifications requested by an Applicant, modify the RFP document by the issuance of Addendum/ Amendment and posting it on the Official Website and by conveying the same to the prospective Applicants by fax or e-mail.

    - All such amendments will be notified in writing through fax or e-mail to all Applicants. The amendments will also be posted on the Official Website along with the revised RFP containing the amendments and will be binding on all Applicants.

    - In order to afford the Applicants a reasonable time for taking an amendment into account, or for any other reason, the Authority may, in its sole discretion, extend the Proposal Due Date.

- PREPARATION AND SUBMISSION OF PROPOSAL

  - Language

The Proposal with all accompanying documents (the “Documents”) and all Communications in relation to or concerning the Selection Process shall be in English Language and strictly on the forms provided in this RFP. No supporting document or printed literature shall be submitted with the Proposal unless specifically asked for and in case any of these documents is in another language, it must be accompanied by an accurate translation of the relevant passages in English, in which case, for all purposes of interpretation of the Proposal, the translation in English shall prevail.

  - Format and signing of Proposal

    - The Applicant shall provide all the information sought under this RFP. The Authority would evaluate only those Proposals that are received in the specified forms and complete in all respects.

    - The Applicant shall prepare one original set of the Documents comprising the Proposal (together with originals/ copies of documents required to be submitted along therewith pursuant to this RFP) and clearly marked “ORIGINAL”. In addition, the applicant shall submit 1 (one) copy of the Proposal marked “COPY”. In the event of any discrepancy between the originals and the copies, the original shall prevail.

    - The Proposal shall be typed or written in indelible ink and signed by the authorised signatory of the Applicant who shall initial each page, in blue ink. All the alterations, omissions, additions, or any other amendments made to the Proposal shall be initialed by the person(s) signing the Proposal. The Proposals must be properly signed as detailed below:

- by a duly authorized person holding the Power of Attorney (the “Authorised Representative”), in case of a Limited Company or a corporation; or

A copy of the Power of Attorney certified under the hands of a director of the Applicant or a notary public on the specified form shall accompany the Proposal.

    - Applicants should note the Proposal Due Date, as specified in Clause 1.8, for submission of Proposals. Applicants are reminded that no supplementary material will be entertained by the Authority, and that evaluation will be carried out only on the basis of Documents received by the closing time of Proposal Due Date as specified in Clause 2.15.1. Applicants will ordinarily not be asked to provide additional material information or documents subsequent to the date of submission, and unsolicited material if submitted will be summarily rejected.

  - Financial Proposal

    - Applicants shall submit the financial proposal in the format provided at Appendix-5 (the “Financial Proposal”) clearly indicating the total cost of the Consultancy in both figures and words, in Indian Rupees, and signed by the Applicant’s authorised signatory. In the event of any difference between figures and words, the amount indicated in words shall be taken into account.

    - While submitting the Financial Proposal, the Applicant shall ensure the following:

- All the costs associated with the assignment shall be included in the Financial Proposal. These shall normally cover remuneration for all the Personnel (Expatriate and Resident, in the field, office etc), accommodation, air fare, equipment, printing of documents, surveys, geo-technical investigations etc (unless Scope Change approved by Uttarakhand Sanskrit Academy). The total amount indicated in the Financial Proposal shall be without any condition attached or subject to on, and shall be final and binding. In case any assumption or condition is indicated in the Financial Proposal, it shall be considered non-responsive and liable to be rejected.

- The Financial Proposal shall be excluding service tax but inclusive of all other taxes.  For the avoidance of doubt, it is clarified that service tax would be paid extra at the rate prevailing at the time of raising the invoices. Further, all payments shall be subject to deduction of taxes at source as per applicable laws.

- Costs shall be expressed in INR.

  - Submission of Proposal

    - The Applicants shall submit the Proposal in hard bound form with all pages numbered serially and by giving an index of submissions. Each page of the submission shall be signed by the Authorized Representative of the Applicant. In case the proposal is submitted on the document downloaded from Official Website, the Applicant shall be responsible for its accuracy and correctness as per the version uploaded by the Authority and shall ensure that there are no changes caused in the content of the downloaded document. In case of any discrepancy between the downloaded or photocopied version of the RFP and the original RFP issued by the Authority, the latter shall prevail.

    - The Proposal will be sealed in an outer envelope which will bear the address of the Authority, RFP for Consultancy as indicated at Clause 1.11.1 and 1.11.3 and the name and address of the Applicant. It shall also bear on top, the following:

“Do not open, except in presence of the Consultancy Agency Evaluation Committee”

If the envelope is not sealed and marked as instructed above, the Authority assumes no responsibility for the misplacement or premature opening of the contents of the Proposal submitted.

    - The aforesaid outer envelope will contain two separate sealed envelopes, one clearly marked ‘Key Submissions’ and the other clearly marked ‘Financial Proposal’. The envelope	marked “Key Submissions” shall contain:

- Application in the prescribed format along with Appendix-2 to 4 and supporting documents;

- Proposal Security as specified in Clause No. 2.18.1

The envelope marked “Financial Proposal” shall contain the financial proposal in the prescribed format (Appendix-5).

    - The Key Submissions and Financial Proposal shall be typed or written in indelible ink and signed by the authorised signatory of the Applicant. All pages of the original Technical Proposal and Financial Proposal must be numbered and initialed by the person or persons signing the Proposal.

    - The completed Proposal must be delivered on or before the specified time on Proposal Due Date. Proposals submitted by fax, telex, telegram or e-mail shall not be entertained.

    - The Proposal shall be made in the Forms specified in this RFP. Any attachment to such Forms must be provided on separate sheets of paper and only information that is directly relevant should be provided. This may include photocopies of the relevant pages of printed documents.

    - The Financial proposal shall be firm throughout the period of performance of the assignment upto and discharge of all obligations of the Applicant under the Agreement.

  - Proposal Due Date

    - Proposal should be submitted before 1300 hrs on the Proposal Due Date Specified at Clause 1.8 at the address provided in Clause 1.11 in the manner and form as detailed in this RFP.

    - The Authority may, in its sole discretion, extend the Proposal Due Date by issuing an Addendum in accordance with Clause 2.10 uniformly for all Applicants.

  - Late Proposals

Proposals received by the Authority after the specified time on Proposal Due Date shall not be eligible for consideration and shall be summarily rejected.

  - Modification/ substitution/ withdrawal of Proposals

    - No Proposal shall be modified, substituted, or withdrawn by the Applicant after its submission as per the provisions of clause 2.14 and 2.15.

  - Proposal Security.

    - The Applicant shall furnish as part of its Proposal, a Proposal Security of 200,000 (Rs Two Lakhs only) in the form of a Demand Draft issued by one of the Nationalised/ Scheduled Banks in India in favour of “Secretary, Uttarakhand Sanskrit Academy, Haridwar”, returnable/refundable not later than 30 days from PDD except in case of the two highest ranked applicants as required in Clause 2.24.1. In the event that the first ranked Applicant commences the assignment as required in Clause 2.27, the second ranked Applicant, who has been kept in reserve, shall be returned/refunded its Proposal Security forthwith, or within 120 days from PDD whichever is earlier	.

    - The Selected Applicant’s Proposal Security shall be returned/refunded upon the Applicant signing the Agreement and completing the deliverables assigned to it for the first 2 (two) months of the contract in accordance with the provisions thereof.

    - Any Proposal not accompanied by the Proposal Security shall be rejected by the Authority as non-responsive.

    - The Authority shall not be liable to pay any interest on the Proposal Security and the same shall be interest free.

    - The Applicant, by submitting its Application pursuant to this RFP, shall be deemed to have acknowledged that without prejudice to the Authority’s any other right or remedy hereunder or in law or otherwise, the Proposal Security shall be forfeited and appropriated by the Authority under the following conditions:

- If an Applicant engages in any of the Prohibited Practices specified in Section 4 of this RFP; or

- If an Applicant withdraws it’s Proposal during the period of its validity as specified in this RFP and as extended by the Applicant from time to time; or

- In the case of the Selected Applicant, if the Applicant fails to clarify or reconfirm its commitments as required vide Clause 2.21.1; or

- In the case of a Selected Applicant, if the Applicant fails to sign the Agreement or commence the assignment as specified in Clause 2.26 and 2.27 respectively; or

- If the Applicant is found to have a Conflict of Interest as specified in Clause 2.2.

- EVALUATION PROCESS

  - Evaluation of Proposals

    - The Authority shall open the Proposals at 1330 hours on the Proposal Due Date, and in the presence of the Applicants who choose to attend. The envelopes marked “Key Submissions” shall be opened first. The envelopes marked “Financial Proposal” shall be kept sealed for opening at a later date.

    - Proposals for which a notice of withdrawal has been submitted in accordance with Clause 2.17 shall not be opened.

    - Prior to evaluation of Proposals, the Authority will determine whether each Proposal is responsive to the requirements of the RFP. A Proposal shall be considered responsive only if:

- It is received in the form specified at Appendix-2 to 4 (Key Submissions);

- it is received by the Proposal Due Date including any extension thereof pursuant to Clause 	2.15;

- it is accompanied by the Proposal Security as specified in Clause 2.18.1.

- it is signed, sealed, hard bound and marked as stipulated in Clause 2.12 and 2.14;

- it is accompanied by the Power of Attorney as specified in Clause 	2.1.4;

- it contains all the information (complete in all respects) as requested in the RFP;

- it does not contain any condition or qualification;

- Applicant is not non-responsive in terms hereof.

    - The Authority reserves the right to reject any Proposal which is nonresponsive and no request for alteration, modification, substitution or withdrawal shall be entertained by the 	Authority in respect of such Proposals.

    - The Authority would subsequently examine and evaluate Proposals in accordance with the Selection Process specified at Clause 1.6 and the criteria set out in Section 3 of this RFP.

    - A date, time 	and venue will be notified to all Applicants for announcing the result of evaluation and opening of Financial 	Proposals. The opening of Financial Proposals shall be done in presence of respective representatives of Applicants who choose 	to be present. The Authority will not entertain any query or clarification from Applicants who fail to qualify at 	any stage of Selection Process. The financial evaluation and final ranking of the Proposals would be carried out in terms of Section 3.

    - Applicants are advised that Selection will be entirely at the discretion of the Authority. Applicants will be deemed to have understood and agreed that no explanation or justification on any aspect of the Selection Process or Selection will be given.

    - Any information contained in the Proposal shall not in any way be construed as binding on the Authority, its agents, successors or assigns, but shall be binding against the Applicant if the Consultancy is subsequently awarded to it.

  - Confidentiality

Information relating to the examination, clarification, evaluation, and recommendation for the selection of Applicants shall not be disclosed to any person who is not officially concerned with the process or is not a retained professional adviser advising the Authority in relation to, or matters arising out of, or concerning the Selection Process. The Authority will treat all information, submitted as part of the Proposal, in confidence and will require all those who have access to such material to treat the same in confidence. The Authority may not divulge any such information unless it is directed to do so by any statutory entity that has the power under law to require its disclosure or is to enforce or assert any right or privilege of the statutory entity and/or the Authority.

  - Clarifications

    - To facilitate evaluation of Proposals, the Authority may, at its sole discretion, seek clarifications from any Applicant regarding its Proposal. Such clarification(s) shall be provided within the time specified by the Authority for this purpose. Any request for clarification(s) and all clarification(s) in response thereto shall be in writing.

    - If an Applicant does not provide clarifications sought under Sub-Clause 2.21.1 above within the specified time, its Proposal shall be liable to be rejected. In case the Proposal is not rejected, the Authority may proceed to evaluate the Proposal by construing the particulars requiring clarification to the best of its understanding, and the Applicant shall be barred from subsequently questioning such interpretation of the Authority.

E. 	APPOINTMENT OF Consultancy Agency

  - Selected Applicant

    - The first ranked Applicant (the “Selected Applicant”) may, if necessary, be invited for clarifications and reconfirmation of commitments and its obligations under this RFP deployment of Key Personnel, methodology and quality of the work plan.

  - Indemnity

The Consultancy Agency shall, subject to the provisions of the Agreement, indemnify the Authority for any direct loss or damage that is caused due to any deficiency in services.

  - Award of Consultancy

After selection, a Letter of Award (the “LOA”) shall be issued, in duplicate, by the Authority to the Selected Applicant and the Selected Applicant shall, within 7 (seven) days of the receipt of the LOA, sign and return the duplicate copy of the LOA in acknowledgement thereof. In the event the duplicate copy of the LOA duly signed by the Selected Applicant is not received by the stipulated date, the Authority may, unless it consents to extension of time for submission thereof, forfeit the Proposal Security of such Applicant, and the next eligible Applicant may be considered.

  - Performance Security

Upon receipt of Letter of Award (LOA) from the Uttarakhand Sanskrit Academy, the successful Applicant shall furnish the Performance Security of an amount equal to 5% of cost of consultancy services/ financial proposal or Rs. 10.00 lakhs (Rupees Ten Lakhs) only whichever is higher, by way of Bank Guarantee for the due performance of the Contract in the format of Performance Security Form given at Annexure-C. The Performance Security shall be furnished by the selected Consultant within the time specified in LOA but prior to execution of Agreement. The validity period of Bank Guarantee of Performance Security shall be 365 days from the date of LOA and the Consultant shall have to provide the extended Bank Guarantee, before the expiry of 365 days, if required, which shall be valid for the period of six months beyond the date of completion of assignment.

  - Execution of Agreement

After acknowledgement of the LOA as aforesaid by the Selected Applicant, it shall execute the Agreement within the period of 21 (Twenty One) days from the date of issuance of LOA. The Selected Applicant shall not be entitled to seek any deviation in the Agreement. If the Selected Applicant fails to submit the Performance Security as per clause 2.25 and fails to sign the Agreement, his proposal Security shall be forfeited and Appropriated by the Authority. In such an event, the Authority may invite the Second Ranked Applicant for negotiations and may issue LOA to him.

  - Commencement of Assignment

The Consultancy Agency shall commence the Services within seven days form the date of signing of the Agreement. If the Consultancy Agency fails to commence the assignment as specified herein, the Authority may, unless it consents to extension of time thereof may forfeit his Proposal Security as well as his Performance Security and appropriate the same in accordance with the provisions of clause 2.18.5 of this RFP and the Agreement.

  - DROP DEAD FEE

- Drop Dead Fee shall be payable to the  Consultancy Agency by the Authority/GoUk if the project is dropped/abandoned or put on hold by the Government for more than one year from the date of last agreed milestones.

- The amount of “Drop Dead Fee” shall be 10% of the remaining consultancy fee as compensation, after the Consultancy Agency has been paid for the work done upto start of drop dead period.

- In case Authority decides to terminate the study after completion of Part-1 of Appendix-1, the above clause on “drop Dead Fee” shall not be applicable [Please also refer para (5) of Appendix-1]

  - Penalty for delay:

If progress of the assignment is not as per the agreed milestones/ deliverables, as referred in Schedule-1 “Terms of Reference’, the Consultancy Agency shall be liable to pay penalty unless, on its written request, the delay is condoned by Consultancy Agency Evaluation Committee, constituted by GoUk, on the justified and valid grounds. For delay 	upto four weeks beyond the milestone/ deliverables fixed (as per the deliverables and time frame indicated in TOR), a penalty equal to 0.25% of  the agreed financial proposal,  beyond four weeks upto eight weeks 0.50% of fees shall be payable to Uttarakhand Sanskrit Academy. In case of delay beyond 8 weeks, the matter will be referred to Consultancy Agency Evaluation Committee whose decision will be final and binding, however, the maximum penalty for delay will not exceed 10% of the agreed financial proposal.

  - Proprietary data

All documents and other information provided by the Authority or submitted by an Applicant to the Authority shall remain or become the property of the Authority. Applicants and the Consultancy Agency, as the case may be, are to treat all information as strictly confidential. The Authority will not return any Proposal or any information related thereto. All information collected, analysed, processed or in whatever manner provided by the Consultancy Agency to the Authority in relation to the Consultancy shall be the property of the Authority.

# CRITERIA FOR EVALUATION

  - Evaluation of Financial Proposal

    - The financial evaluation will be carried out as per this Clause 3.1. Each Financial Proposal will be assigned a financial score (SF). For financial evaluation, the total cost indicated in the Financial Proposal will be considered.

    - The Authority will determine whether the Financial Proposals are complete, unqualified and unconditional. The cost indicated in the Financial Proposal   shall be deemed as final and reflecting the total cost of services. Omissions, if any, in costing any item shall not entitle the firm to be compensated and the liability to fulfill its obligations as per the TOR within the total quoted price shall be that of the Consultancy Agency. The lowest financial proposal (FM) will be given a financial score (SF) of 100 points. The financial scores of other proposals will be computed as follows:

SF = 100 x FM/F

(F = amount of Financial Proposal of the Applicant)

    - The Selected Applicant shall be the First Ranked Applicant (having the highest score). The Second Ranked Applicant shall be kept in reserve and may be invited for negotiations in case the first ranked Applicant withdraws, or fails to comply with the requirements specified in Clause 2.24, 2.25 and 2.26, and 2.27 as the case may be.

# FRAUD AND CORRUPT PRACTICES

  - The Applicants and their respective officers, employees, agents and advisers shall observe the highest standard of ethics during the Selection Process.   Notwithstanding anything to the contrary contained in this RFP, the Authority shall reject a Proposal without being liable in any manner whatsoever to the Applicant, if it determines that the Applicant has, directly or indirectly or through an agent, engaged in corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice (collectively the “Prohibited Practices”) in the Selection Process. In such an event, the Authority shall, without prejudice to its any other rights or remedies, forfeit and appropriate the Proposal Security or Performance Security, as the case may be, as mutually agreed genuine pre-estimated compensation and damages payable to the Authority for, inter alia, time, cost and effort of the Authority, in regard to the RFP, including consideration and evaluation of such Applicant’s Proposal.

  - Without prejudice to the rights of the Authority under Clause 4.1 hereinabove and the rights and remedies which the Authority may have under the LOA or the Agreement, if an Applicant or Consultant, as the case may be, is found by the Authority to have directly or indirectly or through an agent, engaged or indulged in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice during the Selection Process, or after the issue of the LOA or the execution of the Agreement, such 	Applicant or Applicant shall not be eligible to participate in any tender or RFP issued by the Authority during a period of 2 (two) years from the date such Applicant or Consultant, as the case may be, is found by the Authority to have directly or through an agent, engaged or indulged in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice, as the case may be.

  - For the purposes of this Clause, the following terms shall have the meaning hereinafter respectively assigned to them:

- “corrupt practice” means (i) the offering, giving, receiving, or soliciting, directly or indirectly, of anything of value to influence the action of any person connected with the Selection Process  (for avoidance of doubt, offering of employment to or employing or engaging in any manner whatsoever, directly or indirectly, any official of the Authority who is or has been associated in any manner, directly or indirectly with the Selection Process or the LOA or has dealt with matters concerning the

Agreement or arising there from, before or after the execution thereof, at any time prior to the expiry of one year from the date such official resigns or retires from or otherwise ceases to be in the service of the Authority, shall be deemed to constitute influencing the actions of a person connected with the Selection Process; or (ii) engaging in any manner 	whatsoever, whether during the Selection Process or after the issue of the LOA or after the execution of the Agreement, as the case may be, any person in respect of any matter relating to the Project or the LOA or the Agreement, who at any time has been or is a legal, financial or technical consultant/ adviser of the Authority in relation to any matter 	concerning the Project;

- “fraudulent practice” means a misrepresentation or omission of facts or disclosure of incomplete facts, in order to influence the Selection 	Process;

- “coercive practice” means impairing or harming or threatening to impair or harm, directly or indirectly, any persons or property to influence any person’s participation or action in the Selection Process;

- “undesirable practice” means (i) establishing contact with any person connected with or employed or engaged by the Authority with the objective of canvassing, lobbying or in any manner influencing or attempting to influence the Selection Process; or (ii) having a Conflict of Interest; and

- “restrictive practice” means forming a cartel or arriving at any understanding or arrangement among Applicants with the objective of restricting or manipulating a full and fair competition in the Selection Process.

# PRE-PROPOSAL CONFERENCE

  - Pre-Proposal Conference of the Applicants shall be convened at the designated date, time and place. A maximum of two representatives of each Applicant shall be allowed to participate on production of an authority letter from the Applicant.

  - During the course of Pre-Proposal Conference, the Applicants will be free to seek clarifications and make suggestions for consideration of the Authority. The Authority shall endeavour to provide clarifications and such further information as it may, in its sole discretion, consider appropriate for facilitating a fair, transparent and competitive Selection Process.

# MISCELLANEOUS

  - The Selection Process shall be governed by, and construed in accordance with, 	the laws of India and the Courts at Dehradun shall have exclusive jurisdiction over all disputes arising under, pursuant to and/or in connection with the Selection 	Process.

  - The Authority, in its sole discretion and without incurring any obligation or 	liability, reserves the right, at any time, to:

- suspend and/or cancel the Selection Process and/or amend and/or supplement the Selection Process or modify the dates or other terms and conditions relating thereto;

- consult with any Applicant in order to receive clarification or further information;

- retain any information and/or evidence submitted to the Authority by, on behalf of and/or in 	relation to any Applicant; and/or

- independently verify, disqualify, reject and/or accept any and all submissions or other information and/or evidence submitted by or on behalf of any Applicant.

  - It shall be deemed that by submitting the Proposal, the Applicant agrees and releases the 	Authority, its employees, agents and advisers, irrevocably, 	unconditionally, fully and finally 	from any and all liability for claims, losses, damages, costs, expenses or liabilities in any way 	related to or arising from the exercise of any rights and/or performance of any obligations 	hereunder, pursuant hereto and/or in connection herewith and waives any and all rights and/or claims it may have in this respect, whether actual or contingent, whether present or future.

# Payment to the Consultancy Agency

# In consideration of the Services performed by the Consultancy Agency, the Consultancy Agency will be entitled for payment of fees consideration as per following payment schedule with the approval of Consultancy Agency Evaluation Committee appointed by Authority:

| Sl. No. | Stage of Payment | Percentage of Payment of total Financial Proposal Payable |
| --- | --- | --- |
|  | Part 1 of the Assignment |  |
|  | Mobilization Advance | 10% |
|  | Preliminary Development Layout Design | 10% |
|  | Preliminary Report | 10% |
|  | Final Report | 20% |
|  | On approval of Final Report | 50% |
|  | Part 2 of the Assignment |  |
|  | Channel Approvals | 10% |
|  | Approval of Project Works Details, Specifications, Procurement Bid Documents & Contract Documents | 5% |
|  | Approval of Project Equipments Details, Specifications, Procurement Bid Documents & Contract Documents | 5% |
|  | Completion of all work contracts | 10% |
|  | On final Installation & Commissioning of all equipments | 10% |
|  | Completion of hiring process for the Key Personnel of the channel | 10% |
|  | On completion of first official broadcasting | 20% |
|  | Signing of at least 2 contracts for the channel distribution | 10% |
|  | Signing of at least 2 long term advertising contracts for the channel | 10% |
|  | After Successful completion of 2 months of official broadcasting | 10% |

# The payment as per above schedule shall be made to the Consultancy Agency on completion of satisfactory performance (to be decided by Consultancy Agency Evaluation Committee) of all activities/roles/duties upto the stage of payment as indicated in the Deliverables & Time Frame as per TOR.

# Appendix 1

DESCRIPTION OF THE SERVICES (AS PER TOR)

Terms of Reference (TOR)

TERMS OF REFERENCE (TOR) FOR CONSULTANCY SERVICES

- Scope of Services of Consultancy Agency

The scope of services of the selected Consultancy Agency is as under:

- Part 1 : Preparation of Detailed Project Report

- Part 2 : Approval of the Channel & Project Management

- The selected Applicant could outsource any part of activity mentioned above to a technical expert. However the selected Applicant shall at all times remain responsible for the work carried out by technical expert appointed. The Applicant shall disclose the name of technical expert and name of Key Personnel along with their CV’s at the time of submission of the Financial Proposal.

- The Uttarakhand Sanskrit Academy and the Consultancy Service Evaluation Committee appointed for the Project shall review Part 1 of the work undertaken by Applicant.

- On the completion of Part-1, the Authority shall seek approval of funds from Government of Uttarakhand (GoUK) for the project. Based on the approval of the GoUK, the Authority may or may not proceed with the Part 2 of the assignment

- In the event of Uttarakhand Sanskrit Academy decides not to commence Part-2 study, the whole study shall be concluded on final report of Part-1. In such event the clause 2.28 “Drop Dead Fee” shall not be applicable.

Part 1 : Preparation of Detailed Project Report (DPR)

- PROJECT CONCEPT

The Applicant shall prepare detailed project background, rationale for developing the project, scope of project; identify need for Development of Sanskrit Channel in Uttarakhand and approach & methodology adopted for preparation of the DPR.

- PROJECT COMPONENTS

The Applicant shall identify various project components which could be included in the Project.

- Essential Components

The preliminary project components identified by the Authority is as under:

- Construction of Building ( if required)

- Studio(s)

- Production Control Room

- Master Control Room

- Central Apparatus Room

- Graphics and Editing Room

- Playout Automation

- News Room Control System

- Integration Items

- Broadcasting/Uplink systems

- Human Resource Plan

- Content Development Plan

- Marketing Plan

- The DPR shall :

- provide a comprehensive report on roadmap for Development of Sanskrit Channel. The report should be based on the assessment made through critical studies, survey of viewers and other relevant analysis.

- Provide details of DTH operators, Cable System operators, MSOs, IPTV operators, Terrestrial Transmitters Network operators with their areas of coverage, subscribers’ base, subscription details, and other related details, with a view to organize the distribution of Sanskrit Channel through various modes

- Provide all procedural and regulatory assistance for down-linking and Development of Sanskrit channel

- Provide input on the strategy to be adopted by the channel and give assistance in finding the best possible and cost-effective solution for Development of the channel; and

- The following shall be provided by the Applicant:

- Site preparation Details

- Furniture Details & Specifications

- Air Conditioning Details & Specifications

- All electrical connections & UPS Details & Specifications

- Details & Specifications of all necessary equipment required for the project

- The Applicant shall prepare preliminary drawings, layout for the aforesaid project components and submit them to the Authority for their approval. The final drawings, layouts shall be prepared and finalised in consultation with Authority.

- FINANCIAL

The Applicant shall be responsible for preparation of financial model based on the results of the market surveys, designs prepared by its technical team and private sector inputs. The assumptions relating to Capital expenditure (CAPEX), Operation & maintenance (O&M) expenditure, projected revenues etc should be clearly mentioned in its Financial Feasibility study.

The financial analysis should cover the following points in detail:

- Assessment of the financial viability of the projects based on detailed cash flow projections, detailed cost analysis

- Detailed cash flow projections for the project

- Financial structuring

- Financial analysis – return on investment, DSCR etc

- Cost-Benefit analysis for the authority

- Assessment of project sustainability

The applicant shall also be required to suggest possible financing options for the project.

- Assessment of Risk and mitigation plan

The Applicant would identify and explain the various categories of risk that are envisaged in the project. The Applicant would suggest the method to evaluate the overall chances of potential loss and the consequences. The Applicant would propose a plan to control & monitor the risks and plan for contingencies to risks, which occur.

- Legal Aspects

The Applicant would list out & detail all issues related to the project from legal and regulatory aspects. The details shall include the process & procedures required to be completed for the Sanskrit Channel. Applicant shall also point out the available schemes & exception allowed for government agencies.

- Environmental Safeguards

The Applicant would list out environmental safeguards to be followed for the Project and environmental clearances if any required for the Project.

- Time Frame:-

The Applicant shall adhere to the timelines given below. The effort would be to minimize the time as Government’s aim is to start actual work on ground at the earliest. Time schedule for the consultancy work will be as follows:

| Sl.No. | Activity | Elapsed Time from the Date of Signing of the Agreement |
| --- | --- | --- |
|  | Preliminary DPR | 06 weeks |
|  | Final DPR | 02 weeks post approval of preliminary DPR |

Note:

- Applicant shall be required to complete the job, to the satisfaction of the Uttarakhand Sanskrit Academy within the prescribed time frame.

- Any other activity not specifically mentioned but that may be required for the successful project shall have to be undertaken by the Applicant.

Part 2 :  Approval for the Channel & Project Management

- Based on approval of the Part 1 of the project, the Authority shall give clearance for the Part 2 of the assignment. The Part A & Part B of the Part 2 of the project could be conducted simultaneously or in sequential manner, as per the decision of the authority.

- Approval of the Channel

License and other clearances of channel

The Applicant shall assist the Authority in applying for channel license in Ministry of Information & Broadcasting Ministry.  The applicant shall also assist in getting all other clearances required for new channel, including but not limited to :

- Financial Clearances

- MHA Clearances

- Approval of channel from Ministry

- WPC clearance

The applicant shall ensure that all legal & regulatory compliances are obtained for starting the channel within 1 Year from the commencement of the activity or by the time of trial broadcasting of the channel, whichever is earlier.

- Project Management for Development of the channel

The applicant shall be required to provide assistance to the authority for the following tasks for Development of Channel:

- Procurement of all necessary equipments

- Procurement of works from the relevant contractors

- Project Management & supervision for all the works from contractors

- Project Management & supervision of all equipment installation & commissioning.

- Assist in recruitment of Key Personnel for Channel

- Assist in finalizing agreements with Key distribution networks ( Cable, DTH etc.) for the broadcasting of the channel

- Assisting in finalizing advertisement contracts for the channel

- Assist the authority till 2 months after the first official broadcast by the channel, in all related matters.

- Deliverables & Time Frame:-

Deliverables :

- Channel Approvals - Project Works Details, Specifications, Procurement Bid Documents & Contract Documents - Project Equipments Details, Specifications, Procurement Bid Documents & Contract Documents - Completion of all works - Detailed Job Descriptions for Key Personnel for the channel - Completion of hiring process for the Key Personnel of the channel - Installation & Commissioning of all equipments - Official Start of Broadcasting by the channel - Signing of at least 2 contracts for the channel distribution - Signing of at least 2 long term advertising contracts for the channel

The Applicant shall be given maximum 1 year’s time for the completion of Part 2 of the assignment. The timeline for each activity shall be highlighted by the applicant in its detailed proposal. The final timelines shall be firmed up  by the Authority at the beginning of Part 2 of the assignment.

Note:

- Applicant shall be required to complete the job, to the satisfaction of the Uttarakhand Sanskrit Academy, Department of Sanskrit Education with in the prescribed time frame.

- Any other activity not specifically mentioned but that may be required for the successful project development and selection of developer(s) shall have to be undertaken by the Applicant.

# Appendix 2

Letter of Proposal

(On Applicant’s letter head)

To

The Uttarakhand Sanskrit Academy,

Department of Sanskrit Education,

Haridwar

Email : _________________

Ref:  Your Letter no.  --------------------dated----------

Sub:  Engagement of Consultant for Development of Satellite Sanskrit TV Channel

Dear Sir,

We, the undersigned, offer to provide the consulting services for the above in accordance with your RFP dated (insert date), and our Proposal. We are hereby submitting our Proposal, which includes this Eligibility Document, and a Financial Proposal sealed under separate envelopes for the above mentioned work.

We hereby declare that all the information and statements made in this Proposal are true and accept that any misinterpretation contained in it may lead to our disqualification. Our Proposal is binding upon us and subject to the modifications resulting from contract negotiations, if any.

We understand that you are not bound to accept any Proposal you receive.

We remain,

Yours sincerely,

Signatures

(Authorised Signatory)

Name of Firm

Address

# Appendix 3

Statement of Legal Capacity

(To be forwarded on the letter head of the Applicant)

To

To

The Uttarakhand Sanskrit Academy

Haridwar

Email : _________________

SUB.: Engagement of Consultant for Development of Satellite Sanskrit TV Channel

We have read and understood the RFP in respect of the captioned project provided to us by Uttarakhand Sanskrit Academy.

We hereby agree and undertake as under:

Notwithstanding any qualifications or conditions, whether implied or otherwise, contained in our Proposal we hereby represent and confirm that our Proposal is unqualified and unconditional in all respects and we agree to the terms of proposed agreement, draft of which also forms a part of the RFP document provided to us.

We are not barred by Uttarakhand Sanskrit Academy, Government of Uttarakhand, Government of India or any other agency of Government of Uttarakhand / Government of India from participating in the consultancy assignment.

Dated this ___________________ Day of _______________, 2019.

Name of the Applicant

_________________________________

Signature of the Authorized Person

_________________________________

Name of the Authorized Person

Note:

To be signed and submitted by the Applicant

# Appendix 4

Format For Power Of Attorney For Signing The Proposal

(On a Stamp Paper of relevant value)

##### POWER OF ATTORNEY

Know all men by these presents, we ____________ (name and address of the registered office) do hereby constitute, appoint and authorize Mr./Ms. _____________________ (name and address of residence) who is presently employed with us and holding the position of __________________ as our attorney, to do in our name and on our behalf, all such acts, deeds and things necessary in connection with or incidental to our proposal for the Engagement of Consultant for Development of Satellite Sanskrit TV Channel, including signing and submission of all documents and providing information/ responses to Uttarakhand Sanskrit Academy, Department of Sanskrit Education  representing us in all matters before Uttarakhand Sanskrit Academy, Department of Sanskrit Education and generally dealing with Uttarakhand Sanskrit Academy, Department of Sanskrit Education in all matters in connection with our proposal for the said Project.

We hereby agree to ratify all acts, deeds and things lawfully done by our said attorney pursuant to this Power of Attorney and that all acts, deeds and things done by our aforesaid attorney shall and shall always be deemed to have been done by us.

(Signature)

(Name, Title and Address)

I Accept

________________  (Signature)

(Name, Title and Address of the Attorney)

Notes:

- The mode of execution of the Power of Attorney should be in accordance with the procedure, if any, laid down by the applicable law and the charter documents of the executants(s).

- Also, where required, the executants(s) should submit for verification the extract of the charter documents and documents such as a resolution / power of attorney in favour of the Person executing this Power of Attorney for the delegation of power hereunder on behalf of the Applicant.

- In case the Proposal is signed by an authorised Director of the Applicant, a certified copy of the appropriate resolution / document conveying such authority may be enclosed in lieu of the Power of Attorney.

# Appendix 5

FINANCIAL PROPOSAL

Covering Letter (On Applicant’s letter head)

[Location, Date]

| FROM: [Name of Applicant] …………………………………….. …………………………………….. …………………………………….. …………………………………….. | TO: Uttarakhand Sanskrit Academy, Department of Sanskrit Education, Haridwar Email : ______________________ Telefax : ______________ |
| --- | --- |

Dear Sir,

Subject: Engagement of Consultant for Development of Satellite Sanskrit TV Channel

- We, the undersigned, offer to provide the consulting services for the above in accordance with your RFP. Our Financial Proposal for Project is for the sum of Rs................. (____________________________________________ Amount in words) this amount is inclusive of all other taxes but exclusive of service tax.

- Our Financial Proposal shall be binding upon us subject to any modifications resulting from contract negotiations, up to the expiration of the validity period of the Proposal, i.e. ........................... (Date).

- We undertake that in competing for and, if the award is made to us, in executing the above consultancy services, we will strongly observe the laws against fraud and corruption to force in India namely “Prevention of Corruption Act 1988”

- We understand that you are not bound to accept any Proposal you receive.

Yours sincerely,

Authorized Signature:

Name and Title of Signatory:

Name of Firm:

Address